## Sheet1
Chittenden County Homeless Alliance
Strategic Planning Process
Level of Effort Scenarios: Draft 1
2022-11-01
Task | Frequency/Duration | Timeframe | Who/From | Requirement
Zoom hosts - could be | 1.5 hours | Dec - May | Strategic Planning | Zoom license and access
connected to focus group | 15 - 20 meetings |  | or Executive Comm. | to contact list
facilitators
Survey support and host | TBD - start with 2-4 | Dec - April | Strategic Planning | Survey monkey license and
|  |  | or Executive Comm. | ability to keep and store
data securely and
confidentially
Focus Group facilitators | TBD - (9-12) | Jan - March | Strategic Planning | Willingness and comfort
|  | Dec. Prep and | or Executive Comm. | facilitating
training
Focus group participants | 80-100 | Jan - March | Open | None
1.5 hours
Work group facilitators | TBD - (4-8) | March- April | Strategic Planning | Willingness and comfort
|  | Feb. prep and | or Executive Comm. | facilitating
training
Work group participants | TBD (10-20) | March- April | Open | Willingness and interest
in topics
Chittenden County Homeless Alliance
Strategic Planning Process
Level of Effort Scenarios: Draft 1
2022-11-01
Task | Frequency/Duration | Timeframe | Who/From | Requirement
Design and facilitate | TBD (2-3 mtgs.) | Dec - Jan design and | Strategic Planning | Outreach and recruitment
process to engage |  | recruit | Committee and others | experience
individuals with lived |  |  | TBD
experience (small group)
Other Operational Support
Communications host | TBD | continuous effort | TBD | Access to contact list and
ability to format materials
using Alliance logo and
templates
Readers (1st draft) | TBD | early May | TBD | Interest
Editor (draft 2) | TBD | May | TBD | enjoys and is good at
proofing and editing
Develop transition and | TBD (2-3) meetings | May | Strategic Planning
finalization plan |  |  | or Executive Comm.