## Sheet1
Chittenden County Homeless Alliance
Strategic Plan
Timeline
December 2022 - May 2023
Tasks | Dec |  |  | Jan |  |  | Feb |  |  | March |  |  |  | April |  |  |  | May
| 2 | 3 | 4 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Finalize Plan Process |  | x |  | x
Prepare information releases |  |  |  |  | x
Finalize logistics |  |  |  |  | x
Send introductory materials |  |  |  |  | x
Finalize scorecard format | [6 empty] | x
Gather scorecard data
Meet with faciliators
Focus Groups
Outreach and Membership
Data Quality, PIT, and HMIS
NOFA and Ranking
Application Ranking
Strategic Planning | [9 empty] | x
Coordinated Entry
Community Housing Review
Veterans
Housing Retention
Executive
Steering | [7 empty] | x | [9 empty] | x
Open Sessions (may include surveys) | [17 empty] | (2 or 3)
People with lived experience
Comprises continuous effort